## Sheet1
| Jan | Feb |  |  |  | Mar |  |  |  | Apr
| Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2
Concept | bar: Jan Wk4
Project Infrastructure | bar: Jan Wk4
Code Planning (UML) | bar: Feb Wk1
Satellite Model | bar: Feb Wk2 to Feb Wk3
Satellite Physics | bar: Feb Wk3 to Feb Wk4
Hardware Prototype* | bar: Feb Wk4 to Mar Wk2
Attitude Control* | bar: Mar Wk1 to Mar Wk3
Orbital Maneouvres* | bar: Mar Wk2 to Mar Wk3
Priority Handler* | bar: Mar Wk3 to Mar Wk4
System Testing | bar: Mar Wk4 to Apr Wk2
Presentation | bar: Apr Wk1 to Apr Wk2
*includes documentation and unit testing